## Cover
TEST REPORT DOCUMENT
Project Name | SuperMarketBot |  |  | Creator | Nguyễn Quang Huy
Project Code | SMB_SU26 |  |  | Date | 15/09/2026
Document Code | SMB_SU26_Test_Report_v1.0 |  |  | Version | v1.0
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2026-07-15 | v0.1 | Initial Test Plan | A | Initial draft of Test Plan and testing scope | Report 5
2026-08-10 | v0.5 | Integration Test Cases | A | Formulated API, MQTT, SignalR, and AI integration test cases | Report 5
2026-09-01 | v0.9 | System Test Cases | A | Designed System & UI test cases for Web Admin, Staff, Customer, Robot apps | Report 5
2026-09-15 | v1.0 | Final Test Execution | M | Executed all 3 rounds of testing, 100% pass, finalized defect log | Report 5
Note on D10: ====== ID#AAACHLUGih8 (2026-09-15 10:43:31) *A: Add M: Modify D: Delete

## Test Cases
TEST CASE LIST
Project Name |  | SuperMarketBot
Project Code |  | SMB_SU26
Test Environment Setup Description |  | .NET 10.0 SDK ¦ Kestrel 10.0.9 ¦ Python 3.14.3 FastAPI ¦ Azure SQL Database ¦ Expo SDK 57 / React 19 ¦ Mosquitto MQTT v2.0
No | Function Name | Sheet Name | Description | Pre-Condition
1 | Core Backend & AI APIs | Feature 1 | Integration testing of REST APIs, SignalR Hubs, MQTT Waypoints, AI check-in | Backend server online, Azure SQL connected
2 | Web Admin & Staff Web | Feature 2 | System testing of Web Admin Dashboard, Brand Wallet, Shelf Mapping. | Admin & Staff accounts active
3 | Customer & Robot Mobile | Feature 3 | System testing of Customer Mobile App (Face check-in, Cart, Map) and Robot App (Escort, Patrol, Ads) | Android test devices connected, ROS2 bridge active
4 | User Acceptance Scenarios | Feature 4 | End-to-End business journeys: Smart Customer Shopping, Inventory Restock Loop, Robotic Advertising | Physical supermarket arena (3m x 3m, 6 shelves) ready

## Test Statistics
TEST STATISTICS
Project Name | SuperMarketBot |  | Creator |  | Nguyễn Quang Huy
Project Code | Nguyễn Quang Huy |  | Reviewer/Approver |  | Lê Trọng Hiếu
Document Code | Lê Trọng Hiếu |  | Issue Date |  | 2026-09-15 | 2026-09-15
Notes | 15/09/2026
1 | Core Backend REST APIs, SignalR Hubs & AI Microservice | 15 | 0 | 0 | 0 | 15
2 | Web Admin Management & Staff Digital Store Operations
3 | Customer Smart Shopping & Robot Interactive Escort / Patrol
4 | End-to-End Operational Acceptance Scenarios (UAT)
Sub total
| Test coverage |  |  | %
| Test successful coverage |  |  | %

## Feature 1
Feature | Core Backend REST APIs, SignalR Hubs & AI Microservice | [13 empty] | Passed
Test requirement | Validate REST API endpoints, SignalR hubs, MQTT broker contracts, face recognition check-in, and shelf vision scanning. | [13 empty] | Failed
Number of TCs | Core Backend & AI Realtime APIs | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 15 | 0 | 0 | 0 | 15
Round 2 | 15 | 0 | 0 | 0
Round 3 | 15 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Function A: Authentication & Access Control
IT_AUTH_001 | Verify user login with valid credentials returns JWT token and user claims | 1. POST /api/v1/auth/login with valid JSON 2. Inspect response body and headers | HTTP 200 OK, returns access_token, refresh_token, and role='Staff' | User account exists in DB with role 'Staff' | Passed | 2026-08-10 | Nguyễn Anh Hùng | Passed | 2026-08-25 | Nguyễn Anh Hùng | Passed | 2026-09-12 | Nguyễn Anh Hùng
IT_AUTH_002 | Verify protected robot telemetry endpoint rejects requests without Bearer token | 1. GET /api/v1/robots without Authorization header | HTTP 401 Unauthorized with standard error response | Protected endpoint /api/v1/robots exists | Passed | 2026-08-10 | Nguyễn Anh Hùng | Passed | 2026-08-25 | Nguyễn Anh Hùng | Passed | 2026-09-12 | Nguyễn Anh Hùng
Function B: AI Face Recognition & Member Check-in
IT_MBR_001 | Verify face check-in endpoint forwards frame to AI service and retrieves member ID | 1. POST /api/v1/members/face-checkin with base64 image | BE forwards frame to AI service; AI returns similarity 0.85; BE returns member profile | Member 'Nguyen Van A' registered with face embedding | Passed | 2026-08-10 | Nguyễn Quang Huy | Passed | 2026-08-25 | Nguyễn Quang Huy | Passed | 2026-09-12 | Nguyễn Quang Huy
IT_MBR_002 | Verify customer profile retrieval with health tags and dietary restrictions | 1. GET /api/v1/members/1/health-tags | Returns HealthTags: ['DiabeticFriendly', 'LowSodium']; Response matches EF Core model | Member ID 1 seeded with HealthTags | Passed | 2026-08-10 | Nguyễn Quang Huy | Passed | 2026-08-25 | Nguyễn Quang Huy | Passed | 2026-09-12 | Nguyễn Quang Huy
IT_FACE_001 | Verify OpenCV SFace cosine similarity matches registered face embedding within 0.363 threshold | 1. POST /api/v1/ai/match-face with probe image and stored 128-D vector | Returns is_match=true, cosine_distance < 0.363, latency < 25ms | FastAPI AI microservice online; YuNet & SFace models loaded | Passed | 2026-08-10 | Nguyễn Quang Huy | Passed | 2026-08-25 | Nguyễn Quang Huy | Passed | 2026-09-12 | Nguyễn Quang Huy
Function C: Autonomous Navigation & Robot Telemetry
IT_NAV_001 | Verify route planner computes shortest path between Node 1 and Node 4 via Dijkstra | 1. POST /api/v1/navigation/navigate {robotCode:'RB001', startNode:1, targetNode:4} | Returns HTTP 200 OK with route info; MQTT receives NAVIGATE_WAYPOINTS payload with node coordinates | Robot 'RB001' online; Node 1 to 4 reachable | Passed | 2026-08-10 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu
IT_NAV_002 | Verify autonomous patrol dispatch generates sequential photo stops for Shelves 1 to 6 | 1. POST /api/v1/navigation/dispatch-autonomous {flowType:'AutonomousPatrol'} | MQTT receives sequence of 6 waypoints with isPhotoCapture=true and zero playlist | 6 shelves mapped to Nodes 1..6 | Passed | 2026-08-10 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu
IT_NAV_003 | Verify full-map advertising dispatch maps target zone to designated shelf waypoint | 1. POST /api/v1/navigation/dispatch-autonomous {flowType:'FullMapAdvertising'} | MQTT receives 1 stop per zone with non-empty playlist payload from active campaigns | At least 1 active campaign with target zones | Passed | 2026-08-10 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu
IT_MQTT_001 | Verify MqttClientService publishes NAVIGATE_WAYPOINTS payload with QoS 1 | 1. Trigger robot mission 2. Subscribe to smartmarket/robot/RB001/waypoints topic via mosquitto_sub | Broker receives JSON array of waypoints within 50ms; QoS=1 acknowledged | Mosquitto broker running on TCP 1883 | Passed | 2026-08-10 | Nguyễn Anh Hùng | Passed | 2026-08-25 | Nguyễn Anh Hùng | Passed | 2026-08-25 | Nguyễn Anh Hùng
Function D: Advertising Campaigns & Smart Cart Guide
IT_ADS_001 | Verify active campaign filtering excludes expired or budget-depleted campaigns | 1. GET /api/v1/advertising/campaigns/active | Only returns campaigns with StartDate <= Now <= EndDate and RemainingBudget > 0 | 3 seeded campaigns (1 active, 1 expired, 1 zero-budget) | Passed | 2026-08-10 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu
IT_ADS_002 | Verify AdPlayLog telemetry records impressions and calculates remaining balance | 1. POST /api/v1/advertising/play-log {campaignId:1, duration:15, zoneId:1} | Database inserts AD_PLAY_LOG row; CAMPAIGN.RemainingBudget deducted by costPerPlay | Campaign 1 has RemainingBudget = 500,000 VND | Passed | 2026-08-10 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu
IT_ADS_003 | Verify robot route matches active campaigns targeted to Zone A and delivers video ad payload | 1. GET /api/v1/navigation/robot-playlist?zoneId=1 | Returns JSON playlist containing campaign media URL, duration, and brand sponsor name | Active campaign targeting Zone A; Robot route entering Zone A | Passed | 2026-08-10 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu
IT_CART_001 | Verify AI recipe recommendation ingredients can be added to member cart in batch | 1. POST /api/v1/cart/batch-add with 4 ingredient product IDs | All 4 products added to member cart; Subtotal updated; Out-of-stock items flagged | Recipe 'Canh Chua' has 4 ingredients | Passed | 2026-08-10 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu
IT_CART_002 | Verify CartGuidePlanner optimizes route sequence grouped by shelf ID | 1. POST /api/v1/cart/optimize-route with cart ID | Produces route visiting Shelf 1 once for both items, then Shelf 3, minimizing traversal | Cart contains products on Shelf 1, Shelf 3, and Shelf 1 | Passed | 2026-08-10 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu | Passed | 2026-08-25 | Lê Trọng Hiếu
IT_IMP_001 | Verify product import transaction rolls back on database failure | 1. Upload malformed Excel import file | Transaction rolled back; Zero dirty rows inserted into PRODUCT table | Invalid foreign key in category row | Passed | 2026-08-10 | Nguyễn Quang Huy | Passed | 2026-08-25 | Nguyễn Quang Huy | Passed | 2026-08-25 | Nguyễn Quang Huy
Note on E10: ====== ID#AAACHLUGiiA tqsang (2026-09-15 10:43:31) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Feature 2
Feature | Web Admin Management Portal & Staff Restock Web App | [13 empty] | Passed
Test requirement | Validate Web Admin dashboard, brand advertising wallet, robot fleet telemetry, shelf slot layout, and staff restocking operations. | [13 empty] | Failed
Number of TCs | Web Admin Portal & Staff Management | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 9 | 0 | 0 | 0 | 9
Round 2 | 9 | 0 | 0 | 0
Round 3 | 9 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Function D
Function E: Web Admin Dashboard & 3D Robot Fleet
ST_ADM_001 | Admin login and dashboard statistics visualization | 1. Open http://localhost:5173/login 2. Enter admin credentials 3. Click Login | Redirects to Dashboard; Displays active campaigns, robot fleet status, and revenue cards | Admin account seeded in database | Passed | 2026-09-01 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-08 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-14 | Trần Nguyễn Nhật Khoa
ST_ADM_002 | Brand wallet top-up and balance verification | 1. Navigate to Brand Wallet 2. Enter top-up amount: 10,000,000 VND 3. Confirm payment simulation | Wallet balance increases by 10,000,000 VND; New transaction recorded in history table | Brand manager logged in | Passed | 2026-09-01 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-08 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-14 | Trần Nguyễn Nhật Khoa
ST_ADM_003 | Create targeted Ad Campaign with Zone selection | 1. Open Ad Campaign wizard 2. Upload banner image 3. Select Target Zone: A01 4. Submit | Campaign created in 'Pending' status; Displays in Campaign List with Zone A01 badge | Brand has sufficient wallet balance | Passed | 2026-09-01 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-08 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-14 | Trần Nguyễn Nhật Khoa
ST_ADM_004 | Realtime 2D/3D Robot Fleet Monitoring with Three.js | 1. Open /robot-monitoring page 2. Observe Three.js viewport and telemetry sidebar | Robot 3D model moves in real-time matching MQTT coordinates; Battery and speed update live | Robot RB001 connected and publishing telemetry | Passed | 2026-09-01 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-08 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-14 | Trần Nguyễn Nhật Khoa
ST_ADM_005 | Shelf management visual layout and slot product assignment | 1. Open /shelf-management 2. Select Shelf 2 3. Assign 'Bia Nobilis' to Slot K2_T1_2 | Slot K2_T1_2 displays updated product image and title; Changes persisted to backend | 6 shelves configured in database | Passed | 2026-09-01 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-08 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-14 | Trần Nguyễn Nhật Khoa
Function F: Staff Restock Management & Inventory Loop
ST_STF_001 | Staff authentication and session persistence across app restarts | 1. Open Staff App 2. Enter staff credentials 3. Restart application | Logs in successfully; On restart, SecureStore restores token without re-login prompt | Staff account active | Passed | 2026-09-01 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-08 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-14 | Trần Nguyễn Nhật Khoa
ST_STF_002 | Scan shelf barcode and view real-time slot inventory status | 1. Tap 'Scan Shelf' button 2. Scan ArUco / Barcode for Shelf 3 3. View slot matrix | App renders Shelf 3 with 2 levels, 6 slots; Out-of-stock items highlighted in red | Camera permission granted | Passed | 2026-09-01 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-08 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-14 | Trần Nguyễn Nhật Khoa
ST_STF_003 | Receive low-stock push notification and accept restock assignment | 1. Simulate product quantity = 0 2. Check notification tray 3. Tap notification | Notification received; Deep-links to Restock Task screen with target shelf and slot highlighted | Background notification service running | Passed | 2026-09-01 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-08 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-14 | Trần Nguyễn Nhật Khoa
ST_STF_004 | Confirm item replenishment at shelf slot and sync stock count to backend | 1. Enter restock quantity: 24 2. Tap 'Confirm Restock' 3. Verify backend database | App shows success toast; Database PRODUCT_SLOT quantity updated; Admin dashboard reflects new count | Restock task assigned to staff | Passed | 2026-09-01 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-08 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-14 | Trần Nguyễn Nhật Khoa
Note on E10: ====== ID#AAACHLUGif8 tqsang (2026-09-15 10:43:31) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Feature 3
Feature | Customer Mobile App & Autonomous Robot Android App | [13 empty] | Passed
Test requirement | Validate Customer face check-in, dynamic shopping list, Dijkstra navigation, and Robot screen greeting, escorting, patrol, and zone ad playback. | [13 empty] | Failed
Number of TCs | Customer Mobile App & Autonomous Robot Client | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 8 | 0 | 0 | 0 | 8
Round 2 | 8 | 0 | 0 | 0
Round 3 | 8 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Function G: Customer Mobile Application (Face ID & Smart Cart)
ST_MOB_001 | Customer face check-in via mobile front camera | 1. Tap 'Face Check-in' 2. Align face in preview box 3. Wait for greeting | Face captured, normalized to 640px, matched within 1.2s; Navigates to Home with customer greeting | Customer face registered in system | Passed | 2026-09-01 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-08 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-14 | Nguyễn Hoàng Trường Duy
ST_MOB_002 | Browse AI meal suggestions and add recipe ingredients to dynamic cart | 1. Open 'Meal Ideas' 2. Select 'Canh Chua Ca' 3. Tap 'Add All Ingredients to Cart' | Cart drawer opens showing 4 ingredients; Missing items marked; Total estimated cost calculated | Network connected; Recipes available | Passed | 2026-09-01 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-08 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-14 | Nguyễn Hoàng Trường Duy
ST_MOB_003 | In-store interactive map rendering and item route visualization | 1. Tap 'Guide Me' 2. View 2D supermarket floorplan with optimal waypoint sequence | Map renders 3 zones and 6 shelves; Dijkstra path drawn as polyline from current position to items | Cart contains >= 1 product | Passed | 2026-09-01 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-08 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-14 | Nguyễn Hoàng Trường Duy
ST_MOB_004 | Offline cart caching and reconnection synchronization | 1. Turn on Airplane mode 2. Add items to cart 3. Turn off Airplane mode | Items cached locally in SQLite; Upon reconnection, cart syncs to server without data loss | Customer logged in | Passed | 2026-09-01 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-08 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-14 | Nguyễn Hoàng Trường Duy
Function H: Autonomous Robot Screen & Ad Escort Flow
ST_ROB_001 | Robot welcome screen face recognition and customer greeting | 1. Customer approaches robot camera 2. Observe robot display | Display switches from Standby to Greeting; Shows customer name and recommended shopping list | Robot in Standby mode at entrance | Passed | 2026-09-01 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-08 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-14 | Nguyễn Hoàng Trường Duy
ST_ROB_002 | Escort mode path execution and real-time obstacle avoidance stop | 1. Customer taps 'Escort to Shelf 3' 2. Place obstacle in robot path | Robot moves along waypoints; Ultrasonic/LiDAR stops robot 50cm from obstacle; Resumes when clear | Robot battery > 20%; Motor driver OK | Passed | 2026-09-01 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-08 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-14 | Nguyễn Hoàng Trường Duy
ST_ROB_003 | Autonomous patrol mode and camera shelf photo capture | 1. Dispatch Patrol mission from Admin 2. Observe robot stopping at Shelf 1 to 6 | Robot stops at each shelf tag, triggers camera snapshot, and uploads image to /api/v1/shelf-scans | AutonomousPatrol route active | Passed | 2026-09-01 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-08 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-14 | Nguyễn Hoàng Trường Duy
ST_ROB_004 | Zone-triggered advertising video playback with TTS voiceover | 1. Robot enters Zone A01 2. Observe robot secondary screen | Video ad plays for 15s; Vietnamese TTS announces promotional discount; Impression logged | Active campaign mapped to Zone A01 | Passed | 2026-09-01 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-08 | Nguyễn Hoàng Trường Duy | Passed | 2026-09-14 | Nguyễn Hoàng Trường Duy
ST_STF_003 | Receive low-stock push notification and accept restock assignment | 1. Simulate product quantity = 0 2. Check notification tray 3. Tap notification | Notification received; Deep-links to Restock Task screen with target shelf and slot highlighted | Background notification service running | Passed | 2026-09-01 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-08 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-14 | Trần Nguyễn Nhật Khoa
ST_STF_004 | Confirm item replenishment at shelf slot and sync stock count to backend | 1. Enter restock quantity: 24 2. Tap 'Confirm Restock' 3. Verify backend database | App shows success toast; Database PRODUCT_SLOT quantity updated; Admin dashboard reflects new count | Restock task assigned to staff | Passed | 2026-09-01 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-08 | Trần Nguyễn Nhật Khoa | Passed | 2026-09-14 | Trần Nguyễn Nhật Khoa

## Feature 4
Feature | End-to-End User Acceptance Test Scenarios (Customer, Staff & Brand Journeys) | [13 empty] | Passed
Test requirement | Validate complete real-world business flows across all integrated software modules and physical supermarket arena hardware. | [13 empty] | Failed
Number of TCs | User Acceptance Testing (End-to-End Journeys) | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 3 | 0 | 0 | 0 | 3
Round 2 | 3 | 0 | 0 | 0
Round 3 | 3 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Function I: End-to-End User Acceptance Testing
UAT_SCENARIO_001 | Seamless In-Store Customer Shopping Experience | 1. Customer walks into supermarket 2. Face check-in at Robot or App 3. Select AI meal suggestion 'Canh Chua' 4. Robot escorts customer to Shelf 1 and Shelf 3 5. Add items to cart 6. Complete payment | All steps complete with zero exceptions; Navigation route optimal; Cart totals correct; Biometrics matched within 1.5s | Supermarket arena setup (3m x 3m, 6 shelves); Robot RB001 ready; Test user profile active | Passed | 2026-09-15 | Nguyễn Quang Huy | Passed | 2026-09-15 | Nguyễn Quang Huy | Passed | 2026-09-15 | Nguyễn Quang Huy
UAT_SCENARIO_002 | Automated Shelf Restocking & Inventory Reconciliation | 1. Robot executes patrol scan across Shelves 1..6 2. AI detects out-of-stock item at Slot K2_T1_1 3. Push alert sent to Staff App 4. Staff scans shelf barcode, restocks 20 units, confirms on app 5. Admin dashboard updates live | End-to-end restock loop completes under 3 minutes; Stock count perfectly synchronized across AI, Staff App, and DB | AI service online; Shelf vision model calibrated; Staff user authenticated | Passed | 2026-09-15 | Nguyễn Quang Huy | Passed | 2026-09-15 | Nguyễn Quang Huy | Passed | 2026-09-15 | Nguyễn Quang Huy
UAT_SCENARIO_003 | Targeted Autonomous Robot Advertising Campaign | 1. Brand manager deposits 5,000,000 VND into Brand Wallet 2. Create targeted video campaign for Zone A01 3. Robot dispatches in FullMapAdvertising mode 4. Robot enters Zone A01 and displays video ad 5. Ad impression recorded and budget deducted | Campaign lifecycle executes autonomously; Impression logged in database; Remaining budget deducted by exactly costPerPlay | Brand account active; Robot online and listening to MQTT topic | Passed | 2026-09-15 | Nguyễn Quang Huy | Passed | 2026-09-15 | Nguyễn Quang Huy | Passed | 2026-09-15 | Nguyễn Quang Huy